## Sheet1
|  |  |  | Started | Finished | Status
Task Number | Task | Predecessors | Dependencies
Services passed as Parameters
Configuration Options parameters
Mobs Groups, Groups Teaming Up
Global Mob System
Global ID number Generation
Mob Item Slots
Mob Gear Armor and Shields
Armor Type
Weapon Attack Adjustments
Post Combat Cleanup. Flags, reset once per combat
Mob Special Attack/Defense, Magic Resistance
100 | Initiative for Combat |  | 101
101 | Dead Mob Shouldn't Get an Attack unless Simultaneous Initiative | 100
110 | Mob Level |  | 111, 112
111 | Thac0 chart lookup | 110
112 | Savings Throw Tables | 110
120 | Mob Actions |  | 121, 122, 123, 124
121 | Mob Actions - Decisions | 120
122 | Mob Action - Action - Attack Primary Weapon | 120
123 | Mob Action - Action - Attack OffHand Weapon | 120
124 | Mob Action - Action - Attack Ranged Weapon | 120
130 | Mob Actions - Targeting | 120 | 131, 132, 133
131 | Mob Actions - Switch Target | 130
132 | Mob Actions - Move to Target and Attack | 130
133 | Mob Actions - Flee -> Tiggers Free Attacks | 130
Magical Spells/Abilities
Use Magic Item potions, scrolls, wands, misc
Healing
Magic Missile
Burning Hands
Hold Person
Create Undead Skeleton/Zombie
Wand of Magic Missiles -> depends on Magic Missile
Potion - Healing - various
Potion - Heroism
Potion - Invisibility
Potion - Invulnerability
Scroll - protection
Scroll - summoning
Ring - Fire Resistance
Ring - Free Action
Ring - Protection
Cloak of Displacement