## Sheet1
|  |  |  | Started | Finished | Status
Task Number | Task | Predecessors | Dependencies
| Services passed as Parameters | 0
| Configuration Options parameters | 0
| Global Mob System | 0
| Global ID number Generation | 0
| Mob Item Slots | 0
| Mob Gear Armor and Shields | 0
| Armor Type | 0
| Weapon Attack Adjustments | 0
| Post Combat Cleanup. Flags, reset once per combat | 0
| Mob Special Attack/Defense, Magic Resistance | 0
80 | Master Game Loop | 0
90 | Mobs form Groups | 80 | 91
91 | Mobs/Groups Enter BattleGroup | 90 | 92
92 | Multiple Battles In BattleGroup Resolving Simultaneously | 91 | 100
100 | Initiative for Combat | 92 | 101 | 2018-02-14 |  | Work In Progress
101 | Dead Mob Shouldn't Get an Attack unless Simultaneous Initiative | 100
110 | Mob Level | 0 | 111, 112
111 | Thac0 chart lookup | 110
112 | Savings Throw Tables | 110
120 | Mob Actions | 0 | 121, 122, 123, 124
121 | Mob Actions - Decisions | 120
122 | Mob Action - Action - Attack Primary Weapon | 120
123 | Mob Action - Action - Attack OffHand Weapon | 120
124 | Mob Action - Action - Attack Ranged Weapon | 120
130 | Mob Actions - Targeting | 120 | 131, 132, 133
131 | Mob Actions - Switch Target | 130
132 | Mob Actions - Move to Target and Attack | 130
133 | Mob Actions - Flee -> Tiggers Free Attacks | 130
| Magical Spells/Abilities | 0
| Use Magic Item potions, scrolls, wands, misc | 0
| Healing | 0
| Magic Missile | 0
| Burning Hands | 0
| Hold Person | 0
| Create Undead Skeleton/Zombie | 0
| Wand of Magic Missiles -> depends on Magic Missile | 0
| Potion - Healing - various | 0
| Potion - Heroism | 0
| Potion - Super Heroism | 0
| Potion - Invisibility | 0
| Potion - Invulnerability | 0
| Scroll - protection | 0
| Scroll - summoning | 0
| Ring - Fire Resistance | 0
| Ring - Free Action | 0
| Ring - Protection | 0
| Cloak of Displacement | 0